## Slide 1
EEG foundation model — data & indications update
Team update · 8 September 2026
5.0k h
processed & QC-passed
d10 corpus + ICU coma + wave-1 sets
23.5k h
gathered on disk
+18.5k h landed this week, all verified
21 %
of the 110k-h universe
open-source EEG on disk · goal 50 % by EOY
11
new indication lines added
1 processed, 10 raw — see slide 4
• Wave 1 gather is complete and over-delivered. 15 datasets landed since the Aug 16 roadmap, every file checksum- or byte-verified. The MGH sleep corpus alone is 15,300 h under a commercial-OK licence — 3× our entire processed corpus.
• ICU cardiac-arrest coma (I-CARE) is fully processed: 579 patients, 872 h, 5 hospitals, QC passed. First well-powered prognosis benchmark; leave-one-hospital-out design.
• New indication lines: sleep staging & disorders, obstructive sleep apnea with severity, ALS with ALSFRS-R, neonatal HIE severity, routine normal/abnormal EEG, PD staging at 4× scale, post-COVID, SCA2 drug-trial response.
• Metadata chatbot shipped: 40 datasets · 12,821 subjects · 848 fields, tool registry for cohort/feasibility queries, password-protected, 64 automated tests green.
• Two blockers need decisions: the Temple corpus is not on any lab disk we can find, and the Harvard EEG Database is downloadable but non-commercial-only (slide 5).
EEG foundation model · team update · 8 Sep 2026
1

## Slide 2
Roadmap through Q4 2026 — three data waves, each: gather → process → train → evaluate
Solid ✓ = complete · outlined = planned
Gather
Process
Train
Evaluate
Aug
Sep
Oct
Nov
Dec
Jan
✓
WAVE 1
Open clinical cohorts
ICU coma · sleep · OSA · ALS · PD
~23k h gathered, 5k h processed
WAVE 2
Temple Hospital corpus (TUH)
~15,000 patients, ~25k h — the
single largest open clinical set
WAVE 3
Deep-phenotype cohorts (gated)
ELUCID · EMBARC · NSRR · Harvard
~10,000 patients, 1000s of variables
today
Goal: process and train on 50% of open-source EEG by end of year
5k h processed
23.5k h gathered
(raw on disk)
+ Temple ≈ 48k h
+ deep-phenotype ≈ 60k h (EOY)
50% goal
~110,000 hours of
open-source EEG identified
2

## Slide 3
What landed since the Aug 16 roadmap
All open licence. "Verified" = byte-for-byte match with the source listing or archive checksum. Hours are header-exact sums.
Dataset | Subjects | Hours | Labels / metadata | Status
I-CARE cardiac-arrest coma (PhysioNet, 5 hospitals) | 587 | 872 | CPC outcome, age, sex, ROSC, TTM, rhythm | Processed · QC PASS
MGH sleep PSG — PhysioNet/CinC 2018 | 1,983 | 15,261 | sleep stages + arousals (994 nights), age, sex | Raw · verified
Obstructive sleep apnea, multimodal (ds008108) | 142 | ~1,120 | AHI, OSA severity, MoCA, BDI, PSQI, ESS, 4 cognitive tests × 4 visits | Raw · verified
CAP Sleep Database (Parma) | 108 | 993 | 7 sleep-disorder diagnoses, stages, CAP phases | Raw · verified
NMT routine scalp EEG (Pakistan) | 2,417 | 489 | normal / abnormal (neurologist), age, sex; 43 % under 18 | Raw · md5 OK
bigP3BCI (19 BCI studies, 48 ALS patients) | 254 | 267 | ALS diagnosis + ALSFRS-R, age, sex, race | Raw · verified
Cork neonatal HIE (INFANT centre) | 53 | 169 | EEG background severity grade 1–4, seizure flag | Raw · md5 OK
Iowa Parkinson's: resting (ds008768, new 1 Sep) + 4 task sets | 312 + 394 | 145 | MoCA, UPDRS-III, LEDD, disease duration, ON/OFF, longitudinal | Raw · verified
Post-COVID, SCA2 drug trial, sleep-deprivation, anxiety, schizophrenia, LDAEP | 501 | 130 | 41–121 phenotype columns each (SFT context) | Raw · verified
Total | ~6,750 | ~19,450 |  | 
Not obtained: PRED+CT (links now login-gated; 4 of 14 sets outstanding), Guinea-Bissau/Nigeria epilepsy (Zenodo rate-limits our address). Sleep PSG now dominates the raw pool — pretraining mass; the clinical sets are the benchmark and SFT value.
EEG foundation model · team update · 8 Sep 2026
3

## Slide 4
Benchmark: 61 active tasks across 29 indication families
42 run by one command · 19 need their own protocol · 11 new lines being built from this week's data
Today — 61 tasks evaluated on the d10 encoder
13
Dementia & subtyping
AD ×3 cohorts, FTD ×2, MCI, vascular, AD-vs-MCI/VaD/PD/FTD, dementia-vs-MCI
4
Parkinson's
CAUEEG, UCSD, Tel-Aviv external, mortality prognosis
7
Psychiatric
depression ×3, ADHD, HBN p-factor / internalizing / externalizing
4
Seizure & epilepsy
CHB-MIT patient + segment, SIENA, cross-dataset transfer
9
Cognition & severity
MMSE, RAVLT, digit span, Stroop, TMT-B, RPM, BDI ×2, attention
6
Demographics (normative)
sex ×3 cohorts, age ×3 cohorts — our strongest encoder wins
3
Wellness & brain health
normative wellness, out-of-device transfer, 4-axis profile
8
Other neuro / new cohorts
TBI, migraine, MS, first-episode psychosis, post-COVID, ERP, motor, sedation
3
Prognosis
ICU coma outcome, PD mortality, treatment response
4
Retired / quarantined
TBI original (leak), APOE (chance), migraine (n=5), AD-vs-FTD (age)
New lines from this week's data
✓
ICU cardiac-arrest coma outcome
587 pts · 5 hospitals
○
Sleep staging
994 labelled nights
○
Sleep-disorder diagnosis (7-class)
108 patients
○
Obstructive sleep apnea + severity
142 · AHI graded
○
ALS + ALSFRS-R severity
48 ALS patients
○
Neonatal encephalopathy grade
53 neonates
○
Routine EEG normal vs abnormal
2,417 recordings
○
PD staging: MoCA / UPDRS / LEDD
312 subjects
○
Post-COVID sequelae
342 subjects
○
SCA2 drug-trial response
94 subjects
○
Sleep deprivation; trait anxiety
122 subjects
✓ processed & QC-passed ○ raw, splits next
Every task gets a frozen test cohort and a band-power baseline before any number is reported. Separately: ~300 built-but-unwired splits (LEMON blood, personality, cognition) are our deepest untapped label pool.
EEG foundation model · team update · 8 Sep 2026
4

## Slide 5
Blockers and decisions needed
Two of these need a decision from leadership; the rest are applications with multi-week lead times
DECISION
Temple (TUH) corpus — Wave 2 cannot start
Reported as downloaded, but not found on any lab disk we searched (including neighbouring projects). Need the path, or a fresh NEDC pull (572 GB, ~1 day). Ingestion plan is ready: docs/temple_ingestion_plan.md (~6 weeks to processed + QC).
DECISION
Harvard EEG Database (HEEDB) — biggest prize, non-commercial only
109k patients · 284k EEGs · physician reports for 73 %. Downloadable to our servers once credentialed (our "cloud-only" note was wrong). One licence also covers Neurotech (212k h), the Human Sleep Project (119k PSGs) and ELUCID. The DUA prohibits commercial use including AI-model development, with no permission route. Options: academic-only firewalled use, or skip.
ACTION
Gated applications — start this week (2–8 weeks each)
BDSP credentialing (CITI course + licence, no institutional signatory) · EMBARC via NDA (eRA Commons + signing official) · NSRR data-use agreements (SHHS first: mortality outcomes). All non-commercial except NSRR STAGES.
ACTION
Source blocks
PRED+CT links now require a UNM login (4 of 14 sets outstanding → e-mail the author). Zenodo rate-limits our address (Guinea-Bissau/Nigeria epilepsy, 301 subjects → fetch from another host; script ready). Stroke Figshare zip still password-locked.
DONE
Infrastructure
Five parallel S3 downloads wedged the lab share for an hour; downloads are now capped at two streams and every set was re-verified afterwards.
EEG foundation model · team update · 8 Sep 2026
5

## Slide 6
Next four weeks
Wave 1 moves from gather to process → train → evaluate; Temple starts the day a copy lands
Sep 8 – 20
Process
• Convert the 15 raw sets to the training format: PSG path (6–8 mastoid-referenced channels) for MGH sleep, OSA, CAP; standard path for NMT, PD, ALS, HIE.
• QC figure per cohort before anything enters a split — per-site line noise, dead channels, the OSA device-by-group confound.
• Register datasets + merge condition embeddings (never regenerate).
Sep 15 – 30
Freeze test cohorts
• Sleep staging · OSA vs control (device-balanced) · NMT normal/abnormal (its own eval split) · PD detection + staging on Iowa (de-duplicated across the 5 nested accessions) · ALS · HIE grade · ICU-coma leave-one-hospital-out.
• Band-power baseline on every one — a benchmark ships only when the encoder is compared against it.
Oct 1 – 31
Train + evaluate
• Retrain the encoder on d10 + Wave 1 (≈ 23k h, first time sleep PSG is in the diet); score on every fixed test cohort, old and new.
• EEG + language SFT with the new phenotype tables (OSA batteries, PD scales, ALSFRS-R, HIE grades) — the co-training data the metadata chatbot was built to find.
In parallel
Unblock Wave 2 & 3
• Locate or re-pull Temple; run the ingestion plan on arrival.
• Submit BDSP / NDA / NSRR applications once the commercial-use question is settled.
EEG foundation model · team update · 8 Sep 2026
6